## Slide 1
Project Management
PowerPoint presentation to accompany
Heizer, Render, Munson
Operations Management, Twelfth Edition, Global Edition
Principles of Operations Management, Tenth Edition, Global Edition
PowerPoint slides by Jeff Heyl
3

## Slide 2: Outline - Continued
Project Management Techniques: PERT and CPM
Determining the Project Schedule
Variability in Activity Times
A Critique of PERT and CPM

## Slide 3: Learning Objectives
When you complete this chapter you should be able to:
3.1 Use a Gantt chart for scheduling
3.2 Draw AOA and AON networks
3.3 Complete forward and backward passes for a project
3.4 Determine a critical path
3.5 Calculate the variance of activity times

## Slide 4: Importance of Project Management
Bechtel Project Management
  International workforce, construction professionals, cooks, medical personnel, security
  Strategic value of time-based competition
  Quality mandate for continual improvement

## Slide 5: Project Characteristics
Single unit
Many related activities
Difficult production planning and inventory control
General purpose equipment
High labor skills

## Slide 6: Examples of Projects
Building Construction
Research Project

## Slide 7: Management of Projects
Planning - goal setting, defining the project, team organization
Scheduling - relate people, money, and supplies to specific activities and activities to each other
Controlling - monitor resources, costs, quality, and budgets; revise plans and shift resources to meet time and cost demands

## Slide 8: Project Management Activities
Planning
  Objectives
  Resources
  Work break-down structure
  Organization
Scheduling
  Project activities
  Start and end times
  Network
Controlling
  Monitor, compare, revise, action

## Slide 9: Project Planning, Scheduling, and Controlling
Figure 3.1

## Slide 10: Project Planning, Scheduling, and Controlling
Figure 3.1

## Slide 11: Project Planning, Scheduling, and Controlling
Figure 3.1

## Slide 12: Project Planning, Scheduling, and Controlling
Figure 3.1

## Slide 13: Project Planning, Scheduling, and Controlling
Figure 3.1
Budgets
Delayed activities report
Slack activities report
Time/cost estimates
Budgets
Engineering diagrams
Cash flow charts
Material availability details
CPM/PERT
Gantt charts
Milestone charts
Cash flow schedules

## Slide 14: Project Planning
Establishing objectives
Defining project
Creating work breakdown structure
Determining resources
Forming organization

## Slide 15: Project Organization
Often temporary structure
Uses specialists from entire company
Headed by project manager
  Coordinates activities
  Monitors schedule and costs
Permanent structure called ‘matrix organization’

## Slide 16: Project Organization Most Helpful When:
Work can be defined with a specific goal and deadline
The job is unique or somewhat unfamiliar to the existing organization
The work contains complex interrelated tasks requiring specialized skills
The project is temporary but critical to the organization
The project cuts across organizational lines

## Slide 17: A Sample Project Organization
Technician
Project No. 2
Project
Manager
Electrical
Engineer
Computer Engineer
Test
Engineer
Mechanical
Engineer
Project No. 1
Project
Manager
Technician
Marketing
Finance
Human
Resources
Design
Quality
Mgt
Production
President
Figure 3.2

## Slide 18: Matrix Organization
Marketing Operations Engineering Finance
Project 1
Project 2
Project 3
Project 4

## Slide 19: The Role of the Project Manager
Highly visible
Responsible for making sure that:
All necessary activities are finished in order and on time
The project comes in within budget
The project meets quality goals
The people assigned to the project receive motivation, direction, and information

## Slide 20: The Role of the Project Manager
Highly visible
Responsible for making sure that:
All necessary activities are finished in order and on time
The project comes in within budget
The project meets quality goals
The people assigned to the project receive motivation, direction, and information
Project managers should be:
Good coaches
Good communicators
Able to organize activities from a variety of disciplines

## Slide 21: Ethical Issues
Offers of gifts from contractors
Pressure to alter status reports to mask delays
False reports for charges of time and expenses
Pressure to compromise quality to meet schedules
Project managers face many ethical decisions on a daily basis
The Project Management Institute has established an ethical code to deal with problems such as:

## Slide 22: Work Breakdown Structure
Level
1. Project
2. Major tasks in the project
3. Subtasks in the major tasks
4. Activities (or “work packages”) to be completed

## Slide 23: Work Breakdown Structure
Level 4
Compatible with Windows 7
Compatible with Windows Vista
Compatible with Windows XP
1.1.2.3
1.1.2.2
1.1.2.1
(Work packages)
Level 3
Develop GUIs
Design Cost Tracking Reports
Module Testing
Ensure Compatibility with Earlier Versions
Develop Cost/Schedule Interface
Defect Testing
1.1.1
1.2.2
1.3.2
1.3.1
1.2.1
1.1.2
Figure 3.3
Level 2
Software Design
Cost Management Plan
System Testing
1.1
1.2
1.3
Level 1
Develop Windows 8 Operating System
1.0

## Slide 24: Project Scheduling Techniques
Ensure that all activities are planned for
Their order of performance is accounted for
The activity time estimates are recorded
The overall project time is developed

## Slide 25: Purposes of Project Scheduling
Shows the relationship of each activity to others and to the whole project
Identifies the precedence relationships among activities
Encourages the setting of realistic time and cost estimates for each activity
Helps make better use of people, money, and material resources by identifying critical bottlenecks in the project

## Slide 26: Project Management Techniques
Gantt chart
Critical Path Method (CPM)
Program Evaluation and Review Technique (PERT)

## Slide 27: A Simple Gantt Chart
Time
J F M A M J J A S
Design
Prototype
Test
Revise
Production

## Slide 28: Service For a Delta Jet
Figure 3.4
Passengers
Baggage
Fueling
Cargo and mail
Galley servicing
Lavatory servicing
Drinking water
Cabin cleaning
Cargo and mail
Flight services
Operating crew
Baggage
Passengers
Deplaning
Baggage claim
Container offload
Pumping
Engine injection water
Container offload
Main cabin door
Aft cabin door
Aft, center, forward
Loading
First-class section
Economy section
Container/bulk loading
Galley/cabin check
Receive passengers
Aircraft check
Loading
Boarding
0 10 20 30 40
Time, Minutes

## Slide 29: Project Controlling
Close monitoring of resources, costs, quality, budgets
Feedback enables revising the project plan and shift resources
Computerized tools produce extensive reports

## Slide 30: Project Management Software
There are several popular packages for managing projects
  Oracle Primavera
  MindView
  HP Project
  Fast Track
  Microsoft Project

## Slide 31: Project Control Reports
Detailed cost breakdowns for each task
Labor requirements
Cost and hour summaries
Raw materials and expenditure forecasts
Variance reports
Time analysis reports
Work status reports

## Slide 32: PERT and CPM
Network techniques
Developed in 1950s
  CPM by DuPont for chemical plants (1957)
  PERT by Booz, Allen & Hamilton with the U.S. Navy, for Polaris missile (1958)
Consider precedence relationships and interdependencies
Each uses a different estimate of activity times

## Slide 33: Six Steps PERT and CPM
Define the project and prepare the work breakdown structure
Develop relationships among the activities – decide which activities must precede and which must follow others
Draw the network connecting all of the activities

## Slide 34: Six Steps PERT and CPM
Assign time and/or cost estimates to each activity
Compute the longest time path through the network – this is called the critical path
Use the network to help plan, schedule, monitor, and control the project

## Slide 35: Questions PERT and CPM Can Answer
When will the entire project be completed?
What are the critical activities or tasks in the project?
Which are the noncritical activities?
What is the probability the project will be completed by a specific date?

## Slide 36: Questions PERT and CPM Can Answer
Is the project on schedule, behind schedule, or ahead of schedule?
Is the money spent equal to, less than, or greater than the budget?
Are there enough resources available to finish the project on time?
If the project must be finished in a shorter time, what is the way to accomplish this at least cost?

## Slide 37: A Comparison of AON and AOA Network Conventions
Activity on Activity Activity on
Node (AON) Meaning Arrow (AOA)
A comes before B, which comes before C
(a)
A
B
C
B
A
C
A and B must both be completed before C can start
(b)
A
C
C
B
A
B
B and C cannot begin until A is completed
(c)
B
A
C
A
B
C

## Slide 38: A Comparison of AON and AOA Network Conventions
Activity on Activity Activity on
Node (AON) Meaning Arrow (AOA)
C and D cannot begin until both A and B are completed
(d)
A
B
C
D
B
A
C
D
C cannot begin until both A and B are completed
D cannot begin until B is completed
A dummy activity is introduced in AOA
(e)
C
A
B
D
Dummy activity
A
B
C
D

## Slide 39: A Comparison of AON and AOA Network Conventions
Activity on Activity Activity on
Node (AON) Meaning Arrow (AOA)
B and C cannot begin until A is completed
D cannot begin until both B and C are completed
A dummy activity is again introduced in AOA
(f)
A
C
D
B
A
B
C
D
Dummy activity

## Slide 40: AON Example
Table 3.1 | Milwaukee Paper Manufacturing’s Activities and Predecessors |  | 
ACTIVITY |  | DESCRIPTION | IMMEDIATE PREDECESSORS
A |  | Build internal components | —
B |  | Modify roof and floor | —
C |  | Construct collection stack | A
D |  | Pour concrete and install frame | A, B
E |  | Build high-temperature burner | C
F |  | Install pollution control system | C
G |  | Install air pollution device | D, E
H |  | Inspect and test | F, G

## Slide 41: AON Network for Milwaukee Paper
A
Start
B
Start Activity
Activity A
(Build Internal Components)
Activity B
(Modify Roof and Floor)
Figure 3.5

## Slide 42: AON Network for Milwaukee Paper
Figure 3.6
C
D
A
Start
B
Activity A Precedes Activity C
Activities A and B Precede Activity D

## Slide 43: AON Network for Milwaukee Paper
G
E
F
H
C
A
Start
D
B
Arrows Show Precedence Relationships
Figure 3.7

## Slide 44: AOA Network for Milwaukee Paper
H
(Inspect/ Test)
7
Dummy Activity
6
F
(Install Controls)
E
(Build Burner)
G
(Install Pollution Device)
5
D
(Pour Concrete/ Install Frame)
4
C
(Construct Stack)
1
3
2
B
(Modify Roof/Floor)
A
(Build Internal Components)
Figure 3.8

## Slide 45: Determining the Project Schedule
Perform a Critical Path Analysis
The critical path is the longest path through the network
The critical path is the shortest time in which the project can be completed
Any delay in critical path activities delays the project
Critical path activities have no slack time

## Slide 46: Determining the Project Schedule
Table 3.2 | Time Estimates for Milwaukee Paper Manufacturing |  | 
ACTIVITY |  | DESCRIPTION | TIME (WEEKS)
A |  | Build internal components | 2
B |  | Modify roof and floor | 3
C |  | Construct collection stack | 2
D |  | Pour concrete and install frame | 4
E |  | Build high-temperature burner | 4
F |  | Install pollution control system | 3
G |  | Install air pollution device | 5
H |  | Inspect and test | 2
 |  | Total time (weeks) | 25

## Slide 47: Determining the Project Schedule
Perform a Critical Path Analysis
Earliest start (ES) = earliest time at which an activity can start, assuming all predecessors have been completed
Earliest finish (EF) = earliest time at which an activity can be finished
Latest start (LS) = latest time at which an activity can start so as to not delay the completion time of the entire project
Latest finish (LF) = latest time by which an activity has to be finished so as to not delay the completion time of the entire project

## Slide 48: Determining the Project Schedule
Activity Format
Figure 3.9
A
Activity Name or Symbol
Earliest Start
ES
Earliest Finish
EF
Latest Start
LS
Latest Finish
LF
Activity Duration
2

## Slide 49: Forward Pass
Begin at starting event and work forward
Earliest Start Time Rule:
If an activity has only a single immediate predecessor, its ES equals the EF of the predecessor
If an activity has multiple immediate predecessors, its ES is the maximum of all the EF values of its predecessors
ES = Max {EF of all immediate predecessors}

## Slide 50: Forward Pass
Earliest Finish Time Rule:
The earliest finish time (EF) of an activity is the sum of its earliest start time (ES) and its activity time
EF = ES + Activity time
Begin at starting event and work forward

## Slide 51: ES/EF Network for Milwaukee Paper
Start
0
0
ES
0
EF = ES + Activity time

## Slide 52: ES/EF Network for Milwaukee Paper
Start
0
0
0
A
2
2
EF of A = ES of A + 2
0
ES of A

## Slide 53: ES/EF Network for Milwaukee Paper
B
3
Start
0
0
0
A
2
2
0
3
EF of B = ES of B + 3
0
ES of B

## Slide 54: ES/EF Network for Milwaukee Paper
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0

## Slide 55: ES/EF Network for Milwaukee Paper
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
D
4
7
3
= Max (2, 3)

## Slide 56: ES/EF Network for Milwaukee Paper
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0

## Slide 57: ES/EF Network for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
Figure 3.10

## Slide 58: Backward Pass
Begin with the last event and work backwards
Latest Finish Time Rule:
If an activity is an immediate predecessor for just a single activity, its LF equals the LS of the activity that immediately follows it
If an activity is an immediate predecessor to more than one activity, its LF is the minimum of all LS values of all activities that immediately follow it
LF = Min {LS of all immediate following activities}

## Slide 59: Backward Pass
Begin with the last event and work backwards
Latest Start Time Rule:
The latest start time (LS) of an activity is the difference of its latest finish time (LF) and its activity time
LS = LF – Activity time

## Slide 60: LS/LF Times for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
LF = EF of Project
15
13
LS = LF – Activity time

## Slide 61: LS/LF Times for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
13
15
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
LF = Min(LS of following activity)
10
13

## Slide 62: LS/LF Times for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
13
15
10
13
8
13
4
8
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
LF = Min(4, 10)
4
2

## Slide 63: LS/LF Times for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
13
15
10
13
8
13
4
8
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
4
2
8
4
2
0
4
1
0
0

## Slide 64: Computing Slack Time
After computing the ES, EF, LS, and LF times for all activities, compute the slack or free time for each activity
Slack is the length of time an activity can be delayed without delaying the entire project
Slack = LS – ES or Slack = LF – EF

## Slide 65: Computing Slack Time
TABLE 3.3 | Milwaukee Paper’s Schedule and Slack Times |  |  |  |  | 
ACTIVITY | EARLIEST START ES | EARLIEST FINISH EF | LATEST START LS | LATEST FINISH LF | SLACK LS – ES | ON CRITICAL PATH
A | 0 | 2 | 0 | 2 | 0 | Yes
B | 0 | 3 | 1 | 4 | 1 | No
C | 2 | 4 | 2 | 4 | 0 | Yes
D | 3 | 7 | 4 | 8 | 1 | No
E | 4 | 8 | 4 | 8 | 0 | Yes
F | 4 | 7 | 10 | 13 | 6 | No
G | 8 | 13 | 8 | 13 | 0 | Yes
H | 13 | 15 | 13 | 15 | 0 | Yes

## Slide 66: Computing Slack Time
TABLE 3.3 | Milwaukee Paper’s Schedule and Slack Times |  |  |  |  | 
ACTIVITY | EARLIEST START ES | EARLIEST FINISH EF | LATEST START LS | LATEST FINISH LF | SLACK LS – ES | ON CRITICAL PATH
A | 0 | 2 | 0 | 2 | 0 | Yes
B | 0 | 3 | 1 | 4 | 1 | No
C | 2 | 4 | 2 | 4 | 0 | Yes
D | 3 | 7 | 4 | 8 | 1 | No
E | 4 | 8 | 4 | 8 | 0 | Yes
F | 4 | 7 | 10 | 13 | 6 | No
G | 8 | 13 | 8 | 13 | 0 | Yes
H | 13 | 15 | 13 | 15 | 0 | Yes
Activities with zero slack are on the critical path. It:
Starts at the first activity in the project
Terminates at the last activity in the project
Includes only critical activities

## Slide 67: Critical Path for Milwaukee Paper
E
4
F
3
G
5
H
2
4
8
13
15
4
8
13
7
13
15
10
13
8
13
4
8
D
4
3
7
C
2
2
4
B
3
0
3
Start
0
0
0
A
2
2
0
4
2
8
4
2
0
4
1
0
0

## Slide 68: ES – EF Gantt Chart for Milwaukee Paper
A Build internal components
B Modify roof and floor
C Construct collection stack
D Pour concrete and install frame
E Build high-temperature burner
F Install pollution control system
G Install air pollution device
H Inspect and test
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16

## Slide 69: LS – LF Gantt Chart for Milwaukee Paper
A Build internal components
B Modify roof and floor
C Construct collection stack
D Pour concrete and install frame
E Build high-temperature burner
F Install pollution control system
G Install air pollution device
H Inspect and test
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16

## Slide 70: Variability in Activity Times
CPM assumes we know a fixed time estimate for each activity and there is no variability in activity times
PERT uses a probability distribution for activity times to allow for variability

## Slide 71: Variability in Activity Times
Three time estimates are required
  Optimistic time (a) – if everything goes according to plan
  Pessimistic time (b) – assuming very unfavorable conditions
  Most likely time (m) – most realistic estimate

## Slide 72: Variability in Activity Times
Estimate follows beta distribution
Expected activity time:
Variance of activity completion times:
t = (a + 4m + b)/6
v = [(b – a)/6]2

## Slide 73: Variability in Activity Times
Expected activity time:
Variance of activity completion times:
t = (a + 4m + b)/6
v = [(b – a)/6]2
Estimate follows beta distribution
t = (a + 4m + b)/6
v = [(b − a)/6]2
Probability of 1 in 100 of > b occurring
Probability of 1 in 100 of < a occurring
Probability
Optimistic Time (a)
Most Likely
Time (m)
Pessimistic
Time (b)
Activity Time
Figure 3.11

## Slide 74: Computing Variance
TABLE 3.4 |  | Time Estimates (in weeks) for Milwaukee Paper's Project |  |  |  | 
ACTIVITY | OPTIMISTIC a |  | MOST LIKELY m | PESSIMISTIC b | EXPECTED TIME t = (a + 4m + b)/6 | VARIANCE [(b – a)/6]2
A | 1 |  | 2 | 3 | 2 | .11
B | 2 |  | 3 | 4 | 3 | .11
C | 1 |  | 2 | 3 | 2 | .11
D | 2 |  | 4 | 6 | 4 | .44
E | 1 |  | 4 | 7 | 4 | 1.00
F | 1 |  | 2 | 9 | 3 | 1.78
G | 3 |  | 4 | 11 | 5 | 1.78
H | 1 |  | 2 | 3 | 2 | .11

## Slide 75: Probability of Project Completion
Project variance is computed by summing the variances of critical activities
s2 = Project variance
= (variances of activities on critical path)
p

## Slide 76: Probability of Project Completion
Project variance is computed by summing the variances of critical activities
Project variance
s2 = .11 + .11 + 1.00 + 1.78 + .11 = 3.11
Project standard deviation
sp = Project variance
= 3.11 = 1.76 weeks
p

## Slide 77: Probability of Project Completion
PERT makes two more assumptions:
Total project completion times follow a normal probability distribution
Activity times are statistically independent

## Slide 78: Probability of Project Completion
Standard deviation = 1.76 weeks
15 Weeks
(Expected Completion Time)
Figure 3.12

## Slide 79: Probability of Project Completion
What is the probability this project can be completed on or before the 16 week deadline?
Z = – /sp
= (16 weeks – 15 weeks)/1.76
= 0.57
Due Expected date date of completion
Where Z is the number of standard deviations the due date or target date lies from the mean or expected date

## Slide 80: Probability of Project Completion
What is the probability this project can be completed on or before the 16 week deadline?
Z = − /sp
= (16 wks − 15 wks)/1.76
= 0.57
due expected date date of completion
Where Z is the number of standard deviations the due date or target date lies from the mean or expected date
.00 .01 .07 .08
.1 .50000 .50399 .52790 .53188
.2 .53983 .54380 .56749 .57142
.5 .69146 .69497 .71566 .71904
.6 .72575 .72907 .74857 .75175
From Appendix I

## Slide 81: Probability of Project Completion
Time
Probability (T ≤ 16 weeks) is 71.57%
Figure 3.13
0.57 Standard deviations
15 16 Weeks Weeks

## Slide 82: Determining Project Completion Time
Probability of 0.01
Z
Figure 3.14
From Appendix I
Probability of 0.99
2.33 Standard deviations
0
2.33

## Slide 83: Advantages of PERT/CPM
Especially useful when scheduling and controlling large projects
Straightforward concept and not mathematically complex
Graphical networks help highlight relationships among project activities
Critical path and slack time analyses help pinpoint activities that need to be closely watched

## Slide 84: Advantages of PERT/CPM
Project documentation and graphics point out who is responsible for various activities
Applicable to a wide variety of projects
Useful in monitoring not only schedules but costs as well

## Slide 85: Limitations of PERT/CPM
Project activities have to be clearly defined, independent, and stable in their relationships
Precedence relationships must be specified and networked together
Time estimates tend to be subjective and are subject to fudging by managers
There is an inherent danger of too much emphasis being placed on the longest, or critical, path

## Slide 86: Tasks
The activities described by the following table are given for the Howard Corporation in Kansas:
  Draw the appropriate AON PERT diagram for J.C. Howard’s management team.
  Find the critical path.
  What is the project completion time?

## Slide 87: Tasks
Kelle Carpet and Trim installs carpet in commercial offices. Peter Kelle has been very concerned with the amount of time it took to complete several recent jobs. Some of his workers are very unreliable. A list of activities and their optimistic completion time, the most likely completion time, and the pessimistic completion time (all in days) for a new contract are given in the following table:
  Determine the expected completion time and variance for each activity.
  Determine the total project completion time and the critical path for the project.
  Determine ES, EF, LS, LF, and slack for each activity.
  What is the probability that Kelle Carpet and Trim will finish the project in 40 days or less?