## Slide 1
Slides by
.
.
.
.
.
.
.
.
.
.
.
.
John Loucks
St. Edward’s Univ.

## Slide 2: Chapter 13 Project Scheduling: PERT/CPM
Project Scheduling Based on
Expected Activity Times
Project Scheduling Considering
Uncertain Activity Times
Considering Time-Cost Trade-Offs

## Slide 3: PERT/CPM
PERT
  Program Evaluation and Review Technique
  Developed by U.S. Navy for Polaris missile project
  Developed to handle uncertain activity times
CPM
  Critical Path Method
  Developed by DuPont & Remington Rand
  Developed for industrial projects for which activity times generally were known
Today’s project management software packages have combined the best features of both approaches.

## Slide 4: PERT/CPM
PERT and CPM have been used to plan, schedule, and control a wide variety of projects:
  R&D of new products and processes
  Construction of buildings and highways
  Maintenance of large and complex equipment
  Design and installation of new systems

## Slide 5: PERT/CPM
PERT/CPM is used to plan the scheduling of individual activities that make up a project.
Projects may have as many as several thousand activities.
A complicating factor in carrying out the activities is that some activities depend on the completion of other activities before they can be started.

## Slide 6: PERT/CPM
Project managers rely on PERT/CPM to help them answer questions such as:
  What is the total time to complete the project?
  What are the scheduled start and finish dates for each specific activity?
  Which activities are critical and must be completed exactly as scheduled to keep the project on schedule?
  How long can noncritical activities be delayed before they cause an increase in the project completion time?

## Slide 7: Project Network
A project network can be constructed to model the precedence of the activities.
The nodes of the network represent the activities.
The arcs of the network reflect the precedence relationships of the activities.
A critical path for the network is a path consisting of activities with zero slack.

## Slide 8: Example: Frank’s Fine Floats
Frank’s Fine Floats is in the business of building
elaborate parade floats. Frank ‘s crew has a new float to
build and want to use PERT/CPM to help them manage
the project.
The table on the next slide shows the activities that
comprise the project as well as each activity’s estimated
completion time (in days) and immediate predecessors.
Frank wants to know the total time to complete the
project, which activities are critical, and the earliest and
latest start and finish dates for each activity.

## Slide 9: Example: Frank’s Fine Floats
Immediate Completion
Activity Description Predecessors Time (days)
A Initial Paperwork --- 3
B Build Body A 3
C Build Frame A 2
D Finish Body B 3
E Finish Frame C 7
F Final Paperwork B,C 3
G Mount Body to Frame D,E 6
H Install Skirt on Frame C 2

## Slide 10: Example: Frank’s Fine Floats
Project Network
Start
Finish
B
3
D
3
A
3
C
2
G
6
F
3
H
2
E
7

## Slide 11: Earliest Start and Finish Times
Step 1: Make a forward pass through the network as follows: For each activity i beginning at the Start node, compute:
  Earliest Start Time = the maximum of the earliest finish times of all activities immediately preceding activity i. (This is 0 for an activity with no predecessors.)
  Earliest Finish Time = (Earliest Start Time) + (Time to complete activity i ).
The project completion time is the maximum of the Earliest Finish Times at the Finish node.

## Slide 12: Example: Frank’s Fine Floats
Earliest Start and Finish Times
Start
Finish
B
3
D
3
A
3
C
2
G
6
F
3
H
2
E
7
0 3
3 6
6 9
3 5
12 18
6 9
5 7
5 12

## Slide 13: Latest Start and Finish Times
Step 2: Make a backwards pass through the network as follows: Move sequentially backwards from the Finish node to the Start node. At a given node, j, consider all activities ending at node j. For each of these activities, i, compute:
  Latest Finish Time = the minimum of the latest start times beginning at node j. (For node N, this is the project completion time.)
  Latest Start Time = (Latest Finish Time) - (Time to complete activity i ).

## Slide 14: Example: Frank’s Fine Floats
Latest Start and Finish Times
Start
Finish
B
3
D
3
A
3
C
2
G
6
F
3
H
2
E
7
0 3
3 6
6 9
3 5
12 18
6 9
5 7
5 12
6 9
9 12
0 3
3 5
12 18
15 18
16 18
5 12

## Slide 15: Determining the Critical Path
Step 3: Calculate the slack time for each activity by:
Slack = (Latest Start) - (Earliest Start), or
= (Latest Finish) - (Earliest Finish).

## Slide 16: Example: Frank’s Fine Floats
Activity Slack Time
Activity ES EF LS LF Slack
A 0 3 0 3 0 (critical)
B 3 6 6 9 3
C 3 5 3 5 0 (critical)
D 6 9 9 12 3
E 5 12 5 12 0 (critical)
F 6 9 15 18 9
G 12 18 12 18 0 (critical)
H 5 7 16 18 11

## Slide 17: Example: Frank’s Fine Floats
Determining the Critical Path
  A critical path is a path of activities, from the Start node to the Finish node, with 0 slack times.
  Critical Path: A – C – E – G
  The project completion time equals the maximum of the activities’ earliest finish times.
  Project Completion Time: 18 days

## Slide 18: Example: Frank’s Fine Floats
Critical Path
Start
Finish
B
3
D
3
A
3
C
2
G
6
F
3
H
2
E
7
0 3
3 6
6 9
3 5
12 18
6 9
5 7
5 12
6 9
9 12
0 3
3 5
12 18
15 18
16 18
5 12
Critical Path: Start – A – C – E – G – Finish

## Slide 19
Critical Path Procedure
Step 1. Develop a list of the activities that make up the project.
Step 2. Determine the immediate predecessor(s) for each activity in the project.
Step 3. Estimate the completion time for each activity.
Step 4. Draw a project network depicting the activities and immediate predecessors listed in steps 1 and 2.

## Slide 20
Critical Path Procedure
Step 5. Use the project network and the activity time estimates to determine the earliest start and the earliest finish time for each activity by making a forward pass through the network. The earliest finish time for the last activity in the project identifies the total time required to complete the project.
Step 6. Use the project completion time identified in step 5 as the latest finish time for the last activity and make a backward pass through the network to identify the latest start and latest finish time for each activity.

## Slide 21
Critical Path Procedure
Step 7. Use the difference between the latest start time and the earliest start time for each activity to determine the slack for each activity.
Step 8. Find the activities with zero slack; these are the critical activities.
Step 9. Use the information from steps 5 and 6 to develop the activity schedule for the project.

## Slide 22: Uncertain Activity Times
In the three-time estimate approach, the time to complete an activity is assumed to follow a Beta distribution.
An activity’s mean completion time is:
t = (a + 4m + b)/6
  a = the optimistic completion time estimate
  b = the pessimistic completion time estimate
  m = the most likely completion time estimate

## Slide 23
An activity’s completion time variance is:
 2 = ((b-a)/6)2
  a = the optimistic completion time estimate
  b = the pessimistic completion time estimate
  m = the most likely completion time estimate
Uncertain Activity Times

## Slide 24: Uncertain Activity Times
In the three-time estimate approach, the critical path is determined as if the mean times for the activities were fixed times.
The overall project completion time is assumed to have a normal distribution with mean equal to the sum of the means along the critical path and variance equal to the sum of the variances along the critical path.

## Slide 25: Example: ABC Associates
Consider the following project:
Immed. Optimistic Most Likely Pessimistic
Activity Predec. Time (Hr.) Time (Hr.) Time (Hr.)
A -- 4 6 8
B -- 1 4.5 5
C A 3 3 3
D A 4 5 6
E A 0.5 1 1.5
F B,C 3 4 5
G B,C 1 1.5 5
H E,F 5 6 7
I E,F 2 5 8
J D,H 2.5 2.75 4.5
K G,I 3 5 7

## Slide 26: Example: ABC Associates
Project Network
6
4
3
5
5
2
4
1
6
3
5

## Slide 27: Example: ABC Associates
Activity Expected Times and Variances
t = (a + 4m + b)/6  2 = ((b-a)/6)2
Activity Expected Time Variance
A 6 4/9
B 4 4/9
C 3 0
D 5 1/9
E 1 1/36
F 4 1/9
G 2 4/9
H 6 1/9
I 5 1
J 3 1/9
K 5 4/9

## Slide 28: Example: ABC Associates
Earliest/Latest Times and Slack
Activity ES EF LS LF Slack
A 0 6 0 6 0 *
B 0 4 5 9 5
C 6 9 6 9 0 *
D 6 11 15 20 9
E 6 7 12 13 6
F 9 13 9 13 0 *
G 9 11 16 18 7
H 13 19 14 20 1
I 13 18 13 18 0 *
J 19 22 20 23 1
K 18 23 18 23 0 *

## Slide 29: Example: ABC Associates
Determining the Critical Path
  A critical path is a path of activities, from the Start node to the Finish node, with 0 slack times.
  Critical Path: A – C – F – I – K
  The project completion time equals the maximum of the activities’ earliest finish times.
  Project Completion Time: 23 hours

## Slide 30: Example: ABC Associates
Critical Path (A – C – F – I – K)
6
4
3
5
5
2
4
1
6
3
5
0 6
0 6
9 13
9 13
13 18
13 18
9 11
16 18
13 19
14 20
19 22
20 23
18 23
18 23
6 7
12 13
6 9
6 9
0 4
5 9
6 11
15 20

## Slide 31: Example: ABC Associates
Probability the project will be completed within 24 hrs
 2 =  2A +  2C +  2F +  2H +  2K
= 4/9 + 0 + 1/9 + 1 + 4/9
= 2
 = 1.414
z = (24 - 23)/ (24-23)/1.414 = .71
From the Standard Normal Distribution table:
P(z < .71) = .7612

## Slide 32: Example: EarthMover, Inc.
EarthMover is a manufacturer of road construction
equipment including pavers, rollers, and graders. The
company is faced with a new project, introducing a new
line of loaders. Management is concerned that the
project might take longer than 26 weeks to complete
without crashing some activities.

## Slide 33
Immediate Completion
Activity Description Predecessors Time (wks)
A Study Feasibility --- 6
B Purchase Building A 4
C Hire Project Leader A 3
D Select Advertising Staff B 6
E Purchase Materials B 3
F Hire Manufacturing Staff B,C 10
G Manufacture Prototype E,F 2
H Produce First 50 Units G 6
I Advertise Product D,G 8
Example: EarthMover, Inc.

## Slide 34: Example: EarthMover, Inc.
PERT Network
6
4
3
10
3
6
2
6
8

## Slide 35: Example: EarthMover, Inc.
Earliest/Latest Times
Activity ES EF LS LF Slack
A 0 6 0 6 0 *
B 6 10 6 10 0 *
C 6 9 7 10 1
D 10 16 16 22 6
E 10 13 17 20 7
F 10 20 10 20 0 *
G 20 22 20 22 0 *
H 22 28 24 30 2
I 22 30 22 30 0 *

## Slide 36: Example: EarthMover, Inc.
Critical Activities
6
4
3
10
3
6
2
6
8
0 6
0 6
10 20
10 20
20 22
20 22
10 16
16 22
22 30
22 30
22 28
24 30
6 9
7 10
10 13
17 20
6 10
6 10

## Slide 37: Example: EarthMover, Inc.
Crashing
The completion time for this project using normal
times is 30 weeks. Which activities should be crashed,
and by how many weeks, in order for the project to be
completed in 26 weeks?

## Slide 38
Crashing Activity Times
To determine just where and how much to crash activity times, we need information on how much each activity can be crashed and how much the crashing process costs. Hence, we must ask for the following information:
  Activity cost under the normal or expected activity time
  Time to complete the activity under maximum crashing (i.e., the shortest possible activity time)
  Activity cost under maximum crashing

## Slide 39
Crashing Activity Times
In the Critical Path Method (CPM) approach to project scheduling, it is assumed that the normal time to complete an activity, tj , which can be met at a normal cost, cj , can be crashed to a reduced time, tj’, under maximum crashing for an increased cost, cj’.
Using CPM, activity j's maximum time reduction, Mj , may be calculated by: Mj = tj - tj'. It is assumed that its cost per unit reduction, Kj , is linear and can be calculated by: Kj = (cj' - cj)/Mj.

## Slide 40
Example: EarthMover, Inc.
Normal Crash
Activity Time Cost Time Cost
A) Study Feasibility 6 $ 80,000 5 $100,000
B) Purchase Building 4 100,000 4 100,000
C) Hire Project Leader 3 50,000 2 100,000
D) Select Advertising Staff 6 150,000 3 300,000
E) Purchase Materials 3 180,000 2 250,000
F) Hire Manufacturing Staff 10 300,000 7 480,000
G) Manufacture Prototype 2 100,000 2 100,000
H) Produce First 50 Units 6 450,000 5 800,000
I) Advertise Product 8 350,000 4 650,000
Normal Costs and Crash Costs

## Slide 41
Example: EarthMover, Inc.
Normal Crash Time Crash
Activity Time Cost Time Cost Reduction $/Wk
A 6 $ 80,000 5 $100,000 1 $20,000
B 4 100,000 4 100,000 0 ---
C 3 50,000 2 100,000 1 50,000
D 6 150,000 3 300,000 3 50,000
E 3 180,000 2 250,000 1 70,000
F 10 300,000 7 480,000 3 60,000
G 2 100,000 2 100,000 0 ---
H 6 450,000 5 800,000 1 350,000
I 8 350,000 4 650,000 4 75,000
Normal Costs and Crash Costs

## Slide 42
Min 20YA + 50YC + 50YD + 70YE + 60YF + 350YH + 75YI
s.t. YA < 1 XA > 0 + (6 - YA) XG > XF + (2 - YG)
YC < 1 XB > XA + (4 - YB) XH > XG + (6 - YH)
YD < 3 XC > XA + (3 - YC) XI > XD + (8 - YI)
YE < 1 XD > XB + (6 - YD) XI > XG + (8 - YI)
YF < 3 XE > XB + (3 - YE) XH < 26
YH < 1 XF > XB + (10 - YF) XI < 26
YI < 4 XF > XC + (10 - YF)
XG > XE + (2 - YG) Xi, Yj > 0 for all i
Example: EarthMover, Inc.
Linear Program for Minimum-Cost Crashing
Let: Xi = earliest finish time for activity i
Yi = the amount of time activity i is crashed

## Slide 43
Minimum-Cost Crashing Solution
Objective Function Value = $200,000
Variable Value
XA 5.000
XB 9.000
XC 9.000
XD 18.000
XE 16.000
XF 16.000
XG 18.000
XH 24.000
Variable Value
XI 26.000
YA 1.000
YC 0.000
YD 0.000
YE 0.000
YF 3.000
YH 0.000
YI 0.000
Example: EarthMover, Inc.

## Slide 44: End of Chapter 13